* **Attendance** – Please type your name and agency in the chat box.
	+ Kaitlyn Ray (Kate), Dee Dee Ward, Chithra Adams, Joy Varney, Vestena Robbins, Mary Carpenter, Christa Bell, Sherri Staley, Amanda Metcalf, Dyzz Cooper, Tracy Desimone, Chris Cordell, Carol Cecil, Jenny Thornhill, Jennifer Warren, Clarissa Allen, Beth Jordan, Ann Hollen, Katy Mullins, Dr. Lohr
* **Focus on Equity –** Chris has provided DCBS data disaggregated by race and ethnicity by in-home and out-of-home care, examine for possible disproportionality. Chithra has run preliminary analysis, additional data were sent this week. For black/African American under-represented in in-home and over represented in OOHC. Bi- and multi-racial overrepresented in both. Will complete report and look at both underserved as well as disproportionately overserved and discuss potential interventions to address this. GMIT will coordinate activities with those underway through DCBS commissioner’s office. GMIT focus could be on access, use, and outcomes related to behavioral health services for CW population
	+ Include discussion of this when Jennifer, Beth, Tena meet with 2 Commissioners next week.
	+ Lesa Dennis is leading the equity work in DCBS CO.
	+ DCBS has posted position to head up anti-racism efforts
* **Evaluation Update– (**Dr. Chithra Adams) All CMHCs have started completing NOMs
* **Review of SOC FIVE Action Plan –** Discuss developed tasks, leads, and any subcommittees established (attached action plan). All three subcommittees have met several times, developed objectives and tasks for each goal. Below are areas to revisit and/or edit
	+ Goal 1 – (Dee Dee) Infrastructure. Update –
		- Regional GMITs – plan for startup with dates Send Dates to regional team members
		- Consider removing obj 7as it is covered under goal 3
	+ Goal 2 – (Joy)
		- Obj 5 eval team has decided unit of measure to be provider capacity to serve families. Chithra will add unit of measure for each service to evaluation plan and we can attach doc to SmartSheet
		- Obj 7 – revisit this as it is also in Goal 1; respite has both infrastructure and service components
	+ Goal 3 – (Amanda)
		- No edits noted
* **Other – Previous Action Items:**
	+ Project Director Update – interviews will occur week of Sept. 21
* **Agency Updates:**
	+ SKY Readiness Review starting soon (DMS, DCBS, DBHDID)
* **Ideas for upcoming information sharing –**
	+ Kentucky SKY (postpone until new lead staff determined)
* **Next Meeting:** October 9th, 2020 – Microsoft Teams
	+ Dyzz and Amanda deliver Supporting Youth and Families Involved in the Child Welfare System training to the GMIT