**Goal of the Grant:** to improve behavioral health outcomes for children and youth (birth through age 21) who meet criteria for SED and their families and who have child welfare involvement. For this project, child welfare-involved families are those for whom a child abuse and/or neglect investigation results in a substantiation or services-needed finding.

**Purpose of the GMIT:** interagency team responsible for management of the grant, oversight of state and local implementation activities, and ongoing communication with the system of care governing bodies.

|  |
| --- |
| Attendees |
| |  |  |  | | --- | --- | --- | | Barb Greene | Melissa Elliott | Dee Dee Ward | | Dyzz Cooper | Shellie Mills | Amanda Metcalf | | Kasey Slagle-KPFC Peer Support | Billy Fore | Hanna Tucker – DCBS | | Chithra Adams | Kelly Minton – KPFC | Bridgett Rogers – CRBH | | Kelvin Bailey ADANTA | Sherrie Estes ADANTA | Denise Marlett CRBH | | Greta Baker – CRBH |  |  | |

|  |  |  |
| --- | --- | --- |
| 1. Screener/CANS Roll Out | | |
| * Review Process   + Staff to write in-home vs. OOHC at top of page   + Debra will also utilize reports to keep on track. * Screener Brochure: Had small committee meeting to discuss. Assigned sections and will regroup January 2021. * If a child is placed in OOHC after services begin, will CMHC continue NOMS data? | | |
| Action Items | Person Responsible | Deadline |
| Get talking points for CANS update from Dave. | Dee Dee | Jan 2021 |
| Send CANS brochure for parents. | Dee Dee | ASAP |
| Determine if NOMS need to continue if/when youth removed? | Chithra | Feb 2021 |

|  |  |  |
| --- | --- | --- |
| 1. Data & Evaluation | | |
| Data to be discussed regularly at meetings. This information will inform progress.   * Denials or refusal of services. * # of screeners. * # of referrals for CANS. * # of CANS completed. * # Referred to Treatment. * Targeted High Need Services:   + Intensive In-Home   + HFW * Outreach Data – Denise presented KPFC Peer Support services at DCBS Staff meeting in December. KPFC received first referral from Clinton County. | | |
| Action Items | Person Responsible | Deadline |
| Share KPFC brochures and info with DCBS | Barb/KPFC | Feb 2021 |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| 1. **Family & Youth Involvement** | | |
| Regional GMIT Goal Summary - Implement strategies to promote and sustain the voice of children, youth, and their families with child welfare involvement at all levels of the system of care. (Practice, Program, Policy levels)   * How do we get CW involved families to the table?   + KPFC asks families what went well and what didn’t upon completion of services. They also hold focus groups once they have enough families.   + There is a great concern for referring families to sit on groups/committees. Some come away feeling more like the problem than the solution.   + Dyzz & Amanda are charged with supporting, coaching, and mentoring families and youth that want to get involved.   + Agencies could develop family satisfaction surveys – what worked, what didn’t work, ideas for the future.   + CRBH can ask clinicians to discuss with families that have navigated system. * What groups have or need family/youth reps on? What platform options are there? Restorative Justice; FRYSC; DCBS: redesigned CQI meetings, PCC/PCP Meeting, Youth CQI meeting. | | |
| Action Items | Person Responsible | Deadline |
| RIAC members find out if reps are on other platforms | Shellie/Kelvin | Feb 2021 |
| Provide HARTs Ladder Presentation | KPFC | January |
| Reach out to FPP | Hannah | Feb 2021 |

|  |  |  |
| --- | --- | --- |
| 1. Grant Funded Services Update | | |
| SOC FIVE Updates:   * Regional Implementation Specialist Interviews completed 12/18. Request position begin Feb 1. * Service Clarification   + SED Criteria is determined by Clinicians, DCBS does not have to make determination.   + CMHCs are providing services to entire region even though Screeners are being rolled out. Referrals can be made for services to entire region. * Carry Forward amount of $750,000 for Year 2 of grant. Stay tuned.   KPFC   * 7 staff trained in Nurturing Parenting and look to roll out in Feb 2021. * Rolling out SMART Recovery Support Groups online for those in recovery and the support/family of those in recovery. * Looking to complete FAST assessment tools w/ NPP, stay tuned.   CRCC   * Medical Director leaving Dec 31 (Dr. Barbosa). Meeting with another Child Psychiatrist to fill in. * School-based staff still working.   ADANTA   * Awarded Grant funding for Intensive In-Home services. * Still need HFW facilitator and Youth Peer Support Staff but administration has other priorities as this time. Need to educate new administrators of SOC. * RPCs Offering NPP classes virtually in Feb. Currently 60 registered.   Other   * DCBS held FFPSA update. Still need for in-home services. OOHC pop has decreased to 887. FPP hired more staff. | | |
| Action Items | Person Responsible | Deadline |
| Consider/brainstorm ways to educate administration on SOC as a whole and grant as a support. | Dee Dee | January 2021 |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| 1. Training | | |
| National Training Opportunity <https://theinstitute.umaryland.edu/2021traininginstitutes/>   * Carol developed a tip sheet/informational, I’ll be sending in an email. * Please send staff.   SOC Academy June 8-10, 2021 -   * Will be virtual again. * Save the date will be sent soon. * Request for Proposals will be coming soon.   Virtual KY Family Leadership Academy will be held in January 11-13 for Peer Support Specialists. See KPFC website to register and apply. | | |
| Action Items | Person Responsible | Deadline |
| Email TI registration info. | Dee Dee | ASAP |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| 1. Other | | |
| Next Meeting – Please take survey emailed this morning. | | |
| Action Items | Person Responsible | Deadline |
| Take Survey to determine January’s meeting | All | Jan 8, 2021 |
|  |  |  |

**NEXT MEETING**: TBD