**Goal of the Grant:** to improve behavioral health outcomes for children and youth (birth through age 21) who meet criteria for SED and their families and who have child welfare involvement. For this project, child welfare-involved families are those for whom a child abuse and/or neglect investigation results in a substantiation or services-needed finding.

**Purpose of the GMIT:** interagency team responsible for management of the grant, oversight of state and local implementation activities, and ongoing communication with the system of care governing bodies.

|  |
| --- |
| Attendees |
| |  |  |  | | --- | --- | --- | | Sherry Roy-Hunton Lifeskills | Chris Elmore DCBS | Barb Greene KPFC | | Carol Cecil KPFC | Amanda Metcalf KPFC | Jessica Ware UK HDI | | Kate Kirkland UK HDI | Sasha Buckner Lifeskills | Dyzz Cooper KPFC | | Robin Gregory Lifeskills | Gayla Lockhart KPFC | Emilee Nealy Lifeskills | | Jessica Humphrey DCBS | Dawn Crabtree DCBS | Nellie Arnett Bellewood | | Felicia McKisic Bellewood | Joy Varney DBHDID | Christy Probus Audubon | | Chithra Adams UK HDI | Mary Haijner UK HID | Dianne McFarling RVBH | | Katie Sheuer Hopper LIfeskills | Dee Dee Ward BHDID | Anne Embry Lifeskills | | Katrina Crume | Abigail Freeman Lifeskills |  | |

|  |  |  |
| --- | --- | --- |
| 1. **Family & Youth Involvement** | | |
| * HART’s Ladder Presentation – KPFC Carol Cecil & Barb Greene   + What does it mean to you? Nothing about family w/o family.   + Define Family & Youth Driven per SOC on Individual, Program, System levels.   + Shared Checklist   + Assigned worksheet to complete with each agency and discuss at next meeting. * Who and How to get youth & family to this table?   + Anne E will look for reps through RIAC.   + FPP Providers can reach out to those 1 year post services. * Flyer/brochure with additional information | | |
| Action Items | Person Responsible | Deadline |
| Get PSC info to Dawn for DCBS dissemination | Gayla/Katrina | 1/15/21 |
| Present PSC to KY Impact Case Mgrs | Anne | 2/28/20 |
| Present PSC to RIAC meetings | Anne | Feb 2021 |
| Assigned worksheet to complete with each agency and discuss at next meeting. | All | Feb 2021 |
| Share docs for agencies to share with potential reps. | Dee Dee | Jan 30, 2021 |
| Develop an information/invitational packet | Melissa | Feb 4 |

|  |  |  |
| --- | --- | --- |
| 1. Screener/CANS Roll Out | | |
| * Screener Brochure Update - Brochure work subcommittee: Carol, Barb, Dyzz, Amanda, Katy, Chris, Melissa, Jessica, Dee Dee. * DCBS Screener Process –Warren (all 5 ongoing teams) & Henderson Counties (10-12 staff). Chris & Danielle are gatekeepers.   **\*\* Plan to roll out screeners Jan. 1, 2021!** | | |
| Action Items | Person Responsible | Deadline |
|  |  |  |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| 1. Data & Evaluation - Chithra | | |
| * Shared R-GMIT Data Expectations Tip Sheet   + Screeners completed   + Referrals made for CANS   + Number refused Screeners   + CANS completed   + Number of people referred to treatment post CANS | | |
| Action Items | Person Responsible | Deadline |
| Send tip sheet | Dee Dee | 1/15/21 |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| 1. Agency Update | | |
| * Update from SOC – 4 new services awarded in TR Region: IIH, HFW, 24/7 Mobile Crisis, and Respite. Interviews completed and recommendation for hire made for Regional Implementation Specialists. | | |
| Action Items | Person Responsible | Deadline |
|  |  |  |
|  |  |  |

**NEXT MEETING**: Friday, February 1st, 2021, 9:00am Central Time