**Goal of the Grant:** to improve behavioral health outcomes for children and youth (birth through age 21) who meet criteria for SED and their families and who have child welfare involvement. For this project, child welfare-involved families are those for whom a child abuse and/or neglect investigation results in a substantiation or services-needed finding.

**Purpose of the GMIT:** interagency team responsible for management of the grant, oversight of state and local implementation activities, and ongoing communication with the system of care governing bodies.

|  |
| --- |
| Attendees |
| |  |  |  | | --- | --- | --- | | Beth Jordan, DBHDID | Tena Robbins, DBHDID | Dee Dee Ward, DBHDID | | Maxine Reid, DBHDID | Kelly Bradshaw, RVBH | Katie Hopper, Lifeskills | | Joy Varney, DBHDID | Dyzz Cooper, KPFC | Amanda Metcalf, KPFC | | Jessica Humphrey, DCBS | Chris Elmore, DCBS | Danielle Zogg, DCBS | | Robin Gregory, Lifeskills | Anne Embry, Lifeskills | Abbi Freeman, Lifeskills | | Lesley Bentley, RVBH | Jessica Ware, UK | Katie Kirkland, UK | | Chithra Adams, UK | Mary Hajner, UK | Amy Hutchinson, Lifeskills | | Felicia McKisic, Bellewood | Nellie Arnett, Bellewood |  | |

|  |  |  |
| --- | --- | --- |
| 1. **Family & Youth Involvement** | | |
| * Determined we have Youth and Family Reps provided by SOC FIVE grant but need local/regional volunteers. * Who and How to get youth & family to this table?   + Anne E will look for reps through RIAC.   + FPP Providers can reach out to those 1 year post services. * Flyer/brochure with additional information * FPP needs flyer to send out to clients (One-Pager; Charter) by 2-5 | | |
| Action Items | Person Responsible | Deadline |
| Present PSC to KY Impact Case Mgrs | Anne | 2/28/20 |
| Present PSC to RIAC meetings | Anne | Feb 2021 |
| Share docs for agencies to share with potential reps (~~ECC/ECMH; PSC~~; Charter; One Pager) | Dee Dee | Feb 5, 2021 |
| Develop an information/invitational packet | Melissa | Feb 4 |

|  |  |  |
| --- | --- | --- |
| 1. Training Opportunities | | |
| Training Institute Workshops[**https://theinstitute.umaryland.edu/2021traininginstitutes/schedule/**](https://theinstitute.umaryland.edu/2021traininginstitutes/schedule/)   * January’s Kick Off - <https://theinstitute.myabsorb.com/#/curricula/3a7347e9-4a6b-4e53-a04d-b283a66b9c08>   + Building A New Way, Together! featuring Amelia Frank Meyer, Ed.D., CEO & Founder of Alia: Innovations * February’s Options   + 12:30-2:00 CST: Helping Youth & Families During COVID-19: A Trauma Informed Approach or Measuring Implementation of Behavioral Health Services at the State, System, and Program Levels   + 2:30-4:00 CST: State & Organizational Level Strategies for Implementing High Quality, Fidelity Wraparound or The Evolving Landscape of Behavioral Health Technology: Innovations, Applications, and Outcomes. | | |
| Action Items | Person Responsible | Deadline |
|  |  |  |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| 1. SOC FIVE Internal Website | | |
| [Kentucky System of Care V – Improving Outcomes for Children, Youth, and YoungAdults with Mental Health Challenges and their Families (hdiuky.net)](https://urldefense.proofpoint.com/v2/url?u=https-3A__socv.hdiuky.net_&d=DwMF-g&c=jvUANN7rYqzaQJvTqI-69lgi41yDEZ3CXTgIEaHlx7c&r=vvdmQRqAiuDcGaPiU7F_XLazHk28PX23BPOJTCMBmeg&m=fH4FapPknOPJXNWyToXVHIflnd3tAQ4AMBaUAshD2-U&s=1GgSvgR-o0dUEsMiwWTPb7MdQFGknVmua3SCSqCSlcY&e=)  Jessica Ware, UK-HDI, to discuss (email). | | |
| Action Items | Person Responsible | Deadline |
| Review website for discussion. | All | Mar. 1 |

|  |  |  |
| --- | --- | --- |
| 1. Screener/CANS Roll Out | | |
| * DCBS Screener – Beginning with Warren (all 5 ongoing teams) & Henderson Counties (10-12 staff). Chris & Danielle are gatekeepers. * Successes – N/A * Barriers – DCBS screeners not due yet. * Screener Brochure Update – Do you want color copies? DBH will send. * **REMEMBER:** staff can refer families to CMHC for CANS and services with OR without DCBS Screener in every county of the region. Utilize BH referral form, send to CMHC gatekeeper (not DCBS Gatekeeper). | | |
| Action Items | Person Responsible | Deadline |
| Update Screener Brochure and mail color copies. | Dee Dee | Mar1 |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| 1. Data & Evaluation - Chithra | | |
| * Shared R-GMIT Data Expectations Tip Sheet * January 2021 Numbers:   + Policy Changes - 1   + Screeners completed - 0   + Referrals made for CANS - 0   + Number refused Screeners - 0   + CANS completed - 0   + Number of people referred to treatment post CANS - 0 | | |
| Action Items | Person Responsible | Deadline |
|  |  |  |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| 1. Agency Update | | |
| * Update from SOC   + Two Rivers Regional Implementation Specialist will begin March 1-Kelly Bradshaw.   + Cumberland RIS, Maxine Reid, begins Feb. 1.   + ECCs & ECMHs - Referrals can be made by client, healthcare providers, hospitals, DCBS, SU Tx providers, PSS, case mgrs., other. * KPFC – Beginning SMART Recovery in February; PSCs are starting to receive referrals throughout the regions; continuing with Café’s for youth and parents (offering interpreters as well). See website and/or Fb page. * RVBH – LRC leaving at end of month. * Lifeskills – Set up and ready for referrals. * Bellewood – Ready for referrals; no active at this time. Therapists will be receiving Vaccines and begin to offer more in-home/in-person services. | | |
| Action Items | Person Responsible | Deadline |
|  |  |  |
|  |  |  |

**NEXT MEETING**: Monday, March 1st, 2021, 9:00am Central Time