**Goal of the Grant:** to improve behavioral health outcomes for children and youth (birth through age 21) who meet criteria for SED and their families and who have child welfare involvement. For this project, child welfare-involved families are those for whom a child abuse and/or neglect investigation results in a substantiation or services-needed finding.

**Purpose of the GMIT:** interagency team responsible for management of the grant, oversight of state and local implementation activities, and ongoing communication with the system of care governing bodies.

|  |
| --- |
| Attendees |
| |  |  |  | | --- | --- | --- | | Tammi Taylor, DBHDID | Janet Doyel, DCBS | Hannah Hyatt, UK HDI | | Dee Dee Ward, DBHDID | Jennifer Harrell, DCBS | Jessica Ware, UK HDI | | Kelly Bradshaw, DBHDID | Jennifer Polo, DCBS |  | | Kelly Dorman, DBHDID | Susan Rudd, DCBS | Tammy Nalley, TAP | | Maxine Reid, DBHDID | Jennifer Warren, DCBS | Amy Cox, TAP | | Joy Varney, DBHDID | Lizzie Minton, DCBS | Katie Elkins, TAP | |  |  |  | | Serena Eldridge, Pennyroyal Center | Gretchen Roof,  Four Rivers Beh. Health | Kayla Harmon, KPFC | | Rachel Howard, Pennyroyal Center | Wendy Lay,  Four Rivers Beh. Health | Amanda Metcalf, KPFC | |  | Ashlee Brockwell,  Four Rivers Beh. Health |  | |  | Shelley King,  Four Rivers Beh. Health | Monica Futrell,  Heartland Worship | |  |  |  | |

|  |  |  |
| --- | --- | --- |
| 1. **CANS, TWIST & KIDnet- Lizzie Minton** | | |
| Interface between TWIST and KIDnet expanded to include in-home population. Tipsheet for extra step of documenting release of information will be distributed to DCBS staff. CANS assessment results will be accessible by workers through TWIST.   * Work is being done in order to provide a more streamlined method for getting information to providers. * Discussion of Graves County DCBS having extended timeline due to tornado | | |
| Action Items | Person Responsible | Deadline |
| Tammi will contact Renee and Sarah to discuss | Tammi | 12/31/21 |

|  |  |  |
| --- | --- | --- |
| 1. Review DCBS & BHP Implementation Checklist | | |
| DCBS Checklist  A1. Timeline is (Fully in place)   * January screener implementation   A2. Consistent reference documents- (Partially in place)   * Tammi has met with 13 of the 17 DCBS counties in the Lakes region.   A3. Current staffing supports expanded implementation- (Partially in place)  A4. Points of contact (Fully in place)   * Jennifer Polo/ Susan Rudd   A5. Coordinate training w/DCBS staff for in-home screeners- (Fully in place)   * Date for when you’d like to begin adding all youth in the home—vs. targeted youth in the home? (DCBS will assess for expansion by April 2022)   A6. Consistent processes are in place for referrals (Partially in place)   * Wendy is meeting to discuss who will be the best point of contact for Four Rivers. Wendy is currently the point of contact for out of home children * Rachel Howard is the point of contact for Pennyroyal   A7. DCBS offices are aware and have Peer support forms, need to ensure the last four counties are aware (Partially in place)   * Kayla reported four family peer support referrals from Muhlenberg, all the kids are still in the home.   A8. Readiness for outreach- (Partially in place)   * Four DCBS counites need access to brochures   A9. Communication is clear and consistent with BHP (Partially in place)   * Need a liaison for Four Rivers (in-home)—Wendy will be contact person until the in home liaison is named.   A10. Processes exist to identify and adapt policy (Partially in place)   * DCBS would like a process/data to know what in home cases to open weekly instead of monthly * Brainstorm with CQI Specialist   BHP Checklist  B1. Staffing Supports the expansion of implementation   * Pennyroyal- Partially in place, need more trained in CANS * Four Rivers- Partially in place, some staff need to recertify   B2. Consistent reference documents   * Pennyroyal- Partially in place * Four Rivers- Partially in place, would like more reference documents   B3. BHP staff have been identified   * Pennyroyal- Partially in place * Four Rivers- Partially in place   B4. Consistent Intake Process in place to receive referrals   * Pennyroyal- Fully in place, utilize current OOHC process Rachel H. will ensure DCBS has referral forms * Four Rivers- Fully in place   B5. Consistent processes are in place to make referrals for the Peer Support Center   * Pennyroyal hiring Peer support in Jan they have KPFC referral form and information * Four Rivers aware of the services and ready to refer. FRBH has peer support in house, as well.   B6. Processes and Timelines in place for once a CANS referral is received   * Four Rivers- looking at EHR system to identify new vs. existing DCBS clients filter requested a meeting with Dee Dee --can easily adapt EHR system to capture DCBS involvement. * Pennyroyal- need to determine how to identify pop of focus, will reach out to staff   B7. Local/regional outreach methods have been identified.   * Four Rivers & Pennyroyal not in place yet. Looking at developing brochure specific to SOC FIVE & consider meeting with DCBS regularly   B8. Processes exist to identify and adapt policy changes locally/regionally to efficiently deliver SOC services.   * Assess as needed | | |
| Action Items | Person Responsible | Deadline |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| 1. Grant Implementation Procedures- RGMIT Members | | |
| No further questions were raised at this time. | | |
| Action Items | Person Responsible | Deadline |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| 1. Open Discussion- RGMIT Members | | |
| * Website: <https://socv.hdiuky.net/> * If anyone would like a binder, contact Tammi (Amy Cox wants one) * Adult peer support is available, but is not an SOC FIVE service * Shared forms [KPFC Peer Support Referral Form](https://socv.hdiuky.net/shared-files/560/ADJUSTED-KPFC-Peer-Support-Referral-updated-8.23.21.pdf) and [Lakes Flyer for Peer Support](https://view.officeapps.live.com/op/view.aspx?src=https%3A%2F%2Fsocv.hdiuky.net%2Fshared-files%2F599%2FKPFC-Lakes-Region-Peer-Support-Center.docx&wdOrigin=BROWSELINK) | | |
| Action Items | Person Responsible | Deadline |
|  |  |  |
| 1. Action items from November GMIT- Tammi Taylor | | |
| * Janet – no response from CASA yet * Katie Elkins has good rapport with Sanctuary if Tammi would like to speak with them | | |
| Action Items | Person Responsible | Deadline |
|  |  |  |
| 1. State GMIT Meeting Summary/invitation- Dee Dee Ward | | |
| * Lizzie talked about interface expansion between TWIST and KIDnet * Race Equity team – contract updates, training available (contact Tammi/Kelly Bradshaw if interested) * Racial trauma training available * Racial trauma therapy trial (16 weeks, 50 clinicians needed – 25 to use recommended manual and 25 as control group) * Kelly Dorman developing subcommittee to track *respite* for in-home cases, meeting to be scheduled in January (Four Rivers, Tammi and Monica will participate from R-GMIT) * Kentucky Building Bridges Initiative – residential program, funding available for youth/family-oriented agency. Dee Dee will share information * GMIT open to new members- need parent & youth representative * If members have a client/youth they feel is doing well, GMIT would like them in the meetings (small stipend available). Amanda and Dyzz will assist with coaching them.   + Need a youth/parent voice | | |
| Action Items | Person Responsible | Deadline |
|  |  |  |

**NEXT MEETING**: **January 18, 2022 @ 1:30-3:30 CST p.m. ZOOM format**. **SOC Website**:

[Kentucky System of Care V – Improving Outcomes for Children, Youth, and YoungAdults with Mental Health Challenges and their Families (hdiuky.net)](https://urldefense.proofpoint.com/v2/url?u=https-3A__socv.hdiuky.net_&d=DwMF-g&c=jvUANN7rYqzaQJvTqI-69lgi41yDEZ3CXTgIEaHlx7c&r=vvdmQRqAiuDcGaPiU7F_XLazHk28PX23BPOJTCMBmeg&m=fH4FapPknOPJXNWyToXVHIflnd3tAQ4AMBaUAshD2-U&s=1GgSvgR-o0dUEsMiwWTPb7MdQFGknVmua3SCSqCSlcY&e=)