**Goal of the Grant:** to improve behavioral health outcomes for children and youth (birth through age 21) who meet criteria for SED and their families and who have child welfare involvement. For this project, child welfare-involved families are those for whom a child abuse and/or neglect investigation results in a substantiation or services-needed finding.

**Purpose of the GMIT:** interagency team responsible for management of the grant, oversight of state and local implementation activities, and ongoing communication with the system of care governing bodies.

|  |
| --- |
| Attendees |
| |  |  |  | | --- | --- | --- | | Jessica Humphrey | Chris Elmore | Katie Hopper | | Brooke Arnold | Maxine Reid | Lizzie Minton | | Danielle Zogg | Mary Hajner | Dawn Crabtree | | Joy Varney | Katie Kirkland | Dee Dee Ward | | Mary Kay | Jessica Ware | Erix Delgado | | Dr. Brandy Kelly Pryor | Felicia McKisic | Leslie Hughes | | Kelly Dorman | Kelly Bradshaw | Shelly Perdue | | Tammi Taylor | Kevin Garvin |  | |

**Please Note**: A poll was taken during the meeting which indicated more members prefer moving January 3rd meeting to January 10th. **Next meeting will be January 10th.**

|  |  |  |
| --- | --- | --- |
| 1. **Family & Youth Involvement** | | |
| Parent/Youth representative action plan.   * + Anne was not present, Joy reported that she has shared the Parent and Youth Representative Recruitment flyers with Anne prior to the parent retreat.     - Brooke reached out to Dean of students at Kentucky Wesleyan College and will connect Kelly B. | | |
| Action Items | Person Responsible | Deadline |
| Brooke A. will connect Kelly B. to Wesleyan College contact for recruitment of youth representatives. | Brooke A. | 12/30 |

|  |  |  |
| --- | --- | --- |
| 1. Data & Evaluation – Katie Kirkland | | |
| * In the month of November, DCBS data reported: **37** screeners were offered, **1** refusal denial of the screener, **21** referred for CANS assessment, **15** youth who did not screen in for the CANS, **0** refused/denied CANS.   **0** policy changes, **0** outreach efforts  BHP data for November:   * **Number of Policy Changes:**   0 (LifeSkills), 0 (River Valley), 0 (Uspiritus)   * **Number of individuals reached through Outreach Efforts:**   12 (LifeSkills), 0 (River Valley) 20 (Uspiritus)   * **Number of initial CANS assessments completed**:   6 (LifeSkills), 0 (River Valley), 0 (Uspiritus)   * **Number of children/youth NOT referred to services or treatment based on CANS:**   1 (LifeSkills), 0 (River Valley), 0 (Uspiritus)   * **Number of children/youth referred to services or treatment based on CANS:**   5 (LifeSkills), 0 (River Valley), 0 (Uspiritus)   * **Number of children/youth receiving services or treatment after referral:**   6 (LifeSkills), 0 (River Valley), 0 (Uspiritus)   * **Baseline NOMs completed:**   9 (LifeSkills), 0 (River Valley), 0 (Uspiritus)  River Valley can still report numbers if they have not had an opportunity to do so. | | |
| Action Items | Person Responsible | Deadline |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| 1. Highlighting Barriers Discussion in referrals | | |
| * DCBS & CMHC touch-base meetings continue * With staff shortages on both sides of this noted, what are we doing as a RGMIT to move past barriers?   + CMHC: Eased referral process, scanning current caseloads for SOC FIVE qualifications   + DCBS: Invited SOC FIVE to present in staff meetings regarding SOC FIVE services * What more can we do?   + Are there more counties available for SOC FIVE presentation?     - 17 counties in the region and some have multiple teams     - Kelly will send a list of counties and teams who have received the SOC FIVE presentation to DCBS Staff (Dawn and Jessica H.), so Kelly can identify the remaining regions/teams.   + Leslie unable to attend today’s meeting. Leslie is acting as High-Fidelity Wrap coordinator and plans to attend DCBS meetings.     - Mary Kay reported interest in High Fidelity Wrap and follow up occurring. | | |
| Action Items | Person Responsible | Deadline |
| Kelly B. will follow up with DCBS staff to identify counties that have not yet received SOC FIVE presentation. | Kelly B. | 12/30 |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1. SOC FIVE Racial Equity Team | | | | | |
| * Dr. Stephen Kniffley Jr. (Spalding University) Racial Trauma Overview   + Many RGMIT members attended   + Screening training in January, Racial Trauma Therapy training in Feb.   + Email blast going out for Early February on further training. * Timeline review with Dr. Brandy Kelly Pryor held in October: Stakeholder identification upcoming for training selection.   + These selections will include many represented here at RGMIT, who will be tasked with sharing and training others on the team.   + Upcoming update in January | | | | | |
| Action Items | | Person Responsible | | Deadline | |
|  | |  | |  | |
| 1. Other Agency Updates | | | | |
| * SOC FIVE & S-GMIT   + Joy shared resources with the group and encouraged members to think about youth and family recruitment   + This month’s state GMIT we will get an update on KIDNET expansion from Lizzy.   + Partner Funding award letters will be going out   + State GMIT Dr. Kniffley will be providing an update if you are interested; please attend State GMIT this month. * RIAC * Barren River- Anne/Lifeskills **(not present- no update available)** * Green River- Leslie Bentley **(not present- no update available)** * RVBH   + Staffing difficulties ongoing   + Mobile crisis has been very busy and a good referral source and trained to ask if family has DCBS involvement. * Lifeskills   + Recruiting staff, ongoing 2 school districts have agreed to partnership to have clinicians in the schools to help families access services. * DCBS   + Looking for staff to fill vacant positions, cases are higher and less staff daily. * KPFC   + Youth Leadership Academy in January   + Smart Recovery and Nurturing Parent ongoing   + More referrals starting to trickle in from the region * Uspiritus   + Continue to work on receiving referrals, short some positions as well. No further updates. | | | | |
| Action Items | Person Responsible | | Deadline | |
|  |  | |  | |

**NEXT MEETING**: **January 10th @ 9am CST ZOOM format**.

**SOC Website**:

[Kentucky System of Care V – Improving Outcomes for Children, Youth, and YoungAdults with Mental Health Challenges and their Families (hdiuky.net)](https://urldefense.proofpoint.com/v2/url?u=https-3A__socv.hdiuky.net_&d=DwMF-g&c=jvUANN7rYqzaQJvTqI-69lgi41yDEZ3CXTgIEaHlx7c&r=vvdmQRqAiuDcGaPiU7F_XLazHk28PX23BPOJTCMBmeg&m=fH4FapPknOPJXNWyToXVHIflnd3tAQ4AMBaUAshD2-U&s=1GgSvgR-o0dUEsMiwWTPb7MdQFGknVmua3SCSqCSlcY&e=)