# Attendees

**Goal of the Grant:** to improve behavioral health outcomes for children and youth (birth through age 21) who meet criteria for SED and their families and who have child welfare involvement. For this project, child welfare-involved families are those for whom a child abuse and/or neglect investigation results in a substantiation or services-needed finding.

**Purpose of the GMIT:** interagency team responsible for management of the grant, oversight of state and local implementation activities, and ongoing communication with the system of care governing bodies.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ☒ | Chris Elmore | ☐ | Abigail Freeman | ☒ | Debbie Lorence  |
| ☐ | Dawn Crabtree | ☒ | Robin Gregory  | ☐ | Chris Bentonwhite |
| ☐ | Dyzz Cooper | ☐ | Shelly Perdue | ☐ | Anne Embry |
| ☐ | Erix Delgado | ☒ | Katie Kirkland  | ☒ | Dee Dee Ward |
| ☒ | Gayla Lockhart | ☒ | Jessica Ware | ☒ | Tammi Taylor |
| ☐ | Kelly Minton | ☒ | Felicia McKisic | ☐ | Kelly Dorman |
| ☒ | Micah Blelvins | ☐ | Katie Hopper | ☐ | Kelly Bradshaw |
| ☒ | Anita Mattingly | ☒ | Leslie Bentley | ☒ | Maxine Reid  |
| ☐ | ShaDonna Yates | ☒ | Jessica Humphrey | ☐ | Amanda Metcalf  |
| ☐ | Tre Wright | ☒ | Kevin Garvin | ☐ | Brooke Arnold |
| ☒ | Anita Mattingly | ☐ | Kenneth Fletcher | ☒ | Lizzie Minton |
| ☒ | Mary Kay Lamb | ☐ | Amy Hutchinson | ☒ | Melissa Whitley |

☒ = Present ☐ = Absent

**Housekeeping:**

Presentations: If you have an SOC FIVE applicable presentation. Two Rivers RGMIT welcomes you to present to spread the word/network. Youth THRIVE might be available to present to RGMITs

Introducing **SOC FIVE Power Hour**: Once a month learning session with Q & A 3rd Thursday of the month at 12:00p.m. (CST)

# Data Team & Evaluation, UK HDI Team

Katie Kirkland presented the CQI data for June for DCBS and BHPs. Dee Dee asked about the difference in the DCBS numbers on referrals for the CANS Assessment and the number who screened in for the CANS. There was some discussion, but it did not seem there was much incidence of families refusing the CANS once they get referred to the BHPs. A provider representative noted that it is sometimes difficult to reach DCBS workers to follow up on referrals made. Lizzie Minton confirmed that the DCBS worker’s name is on the Referral form (to the BHP). Behavioral health providers seeking contact from a corresponding DCBS worker should cc Chris E. Jessica H. so they can assist workers and ensure follow up.

**Provider Data (June 2022)**

|  |  |  |
| --- | --- | --- |
| CQI Metric | All Regions | Two Rivers |
| Policy Changes | 1 | 0 |
| Individuals reached by Outreach Efforts (as reported) | 142 | 60 |
| Individuals reached by Outreach Efforts (to report to SAMHSA) | 82 | 0 |
| # DCBS Screeners Completed | 143 | 41 |
| # Youth for whom the parent/guardian refused or denied the DCBS Screener | 12 | 12 |
| # Youth Referred for a CANS Assessment based on the DCBS Screener | 32 | 12 |
| # Youth who did not screen in for the CANS Assessment | 89 | 25 |
| # Youth for whom the Parent/Guardian Refused or Denied the CANS Assessment | 13 | 3 |

**Provider Data (June 2022)**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| CQI Metric | All Regions | LifeSkills | River Valley | Uspiritus |
| Policy Changes | 1 | 0 | 0 | 0 |
| Individuals reached by Outreach Efforts (as reported) | 372 | 27 | 6 | 10 |
| Individuals reached by Outreach Efforts (to report to SAMHSA) | 202 | 27 | 4 | 10 |
| # Initial CANS | 22 | 2 | 2 | 0 |
| # NOT referred to services based on CANS | 0 | 0 | 0 | 0 |
| # Referred to Service based on CANS | 24 | 2 | 2 | 2 |
| # Youth receiving services after referral | 20 | 2 | 2 | 2 |
| # Baseline NOMS completed | 5 | 2 | 2 | 0 |

## Action Items

Task Description Person Responsible Deadline

 N/A

# Hope Harbor, Melissa K. Whitley, Executive Director

Crisis center New Beginnings (Crisis services for Two River’s Region)

Hope Harbor’s mission is to empower and support anyone impacted by sexual trauma

Hope Harbor owns a house is in Bowling Green—also space in Logan co and Franklin Co Glasgow

* CDC estimates over 1.2 million people in KY will experience sexual violence in their lifetime.
* Victims of sexual assault are more likely to suffer from depression, PTSD, abuse alcohol/drugs & contemplate suicide.

Services include: 24-hour hotline, legal/systems advocacy, emergency medical advocacy, counseling, referrals, community prevention and education

* Work closely w/ Child Advocacy Center.
* Provide services to secondary victims too.
* Can even be self-referred.
* During Intake paperwork, ask about sexual abuse.
* About 60% clients are adults who have experienced child-hood sexual abuse

**Hope Harbor Services FY 2022 (July 21-June 22)**

Victims served 533

Crisis line calls 290

Hospital advocacy 60

Counseling sessions 2470

Legal advocacy 209

Educational program participants 7056

Professionals Trained 180

* Use state general funds and grants
* Counseling sessions remain telehealth but seeing people in person as well—kids especially

**Community Involvement**

* Sexual assault awareness and prevention month (April)
* Sexual Assault Interagency Council
* Hope Harvest Garden
* Survive to Thrive
* Area Chamber of Commerce
* Multidisciplinary teams in all counties
* Coalition to prevent child abuse
* Community collaborations for children
* Barren River area re-entry task force
* Human trafficking task force

[www.hopeharbor.net](http://www.hopeharbor.net)

## Action Items

Task Description Person Responsible Deadline

N/A

# Progress Updates

Partner Funding Notice of Approvals will be sent this week.

* There are no funds for allotment for October partner funding
* 19 total application from across the state.

Progress areas of improvement:

70 baseline NOMs short of reaching our goal for the grant at the end of September

## Action Items

Task Description Person Responsible Deadline

N/A

# Agency Updates

**DCBS**

* Newly developed DCBS position in Warren County, Court Liaison to attend court
* Always looking to hire, please direct people to apply by region
* 2nd protection specialist on board will join next month

**KPFC**

* Gayla is planning a Leadership Academy, more information coming soon
* Aug 22-23rd Becoming and effective trainer
* Staff retreat in September
* KPFC is starting first Friday of the month webinars 10-12 EST Carmilla will be facilitating <https://kypartnership.org/>

**River Valley Behavioral Health**

* Building high fidelity caseload
* Micah doing great job
* All case management umbrella is moving to a new location at the end of the month, open house forthcoming.

**Uspiritus**

* N/A

**Lifeskills**

* N/A

**SOC FIVE**

ABC Training starting in October offered for SOC FIVE partnering providers. More information forthcoming.

**Racial Equity Change Team**

* + There are still openings available for the Youth Racial Trauma Therapy with Dr. Kniffley. If you are a clinician or know a clinician, please reach out to Dee Dee or register at the link:

[https://urldefense.com/v3/\_\_https:/r20.rs6.net/tn.jsp?f=0010aRHSj9ReFIKfefkO-pdj2aGb8KMbEf5BS4fh7EiqTEvW\_\_dRNtNpU--vPfsFn\_-Hh6jcObnqteXpvx6Vp-kzwzCkLpf00DDbItSoEoXYC2CsMwnw3Vb3vMX\_WgKjgxmgPdsItwVMaYja4BWR7R5dC3n5ejBY0Qz5OhPEYZI58xo2\_wZ7VT7rEGKq1cXzNe4AJzEPcZgfzlQ\_4tBK-baVO1ryHs7\_ZcESgYcWUdRuMTcYBGynDSvJaEPo\_s1TaBmbEy5IGlb4jvqKvJPiMGMiZBsyg8qzBauczka7JEtWT9tpNaYyT3wFNOld0s2UNUiZHHjiQQ5nHQ=&c=vUF\_GRJHmONvu5jXhy\_OGZzJ\_FHVRowK49awbWHqULI1vpK\_iBi8pA==&ch=xs2Cy5eCP53j1WvPbDCuCjjYgJIZghYg63Fj3TZF1ClcTna2v9ad7Q==\_\_;!!Db6frn15oIvDD3UI!1kaZaSkRdtNjnvTSxAO6bK2UV6iXRv-Wcs3cU4pCBSxYMehhll0t2nxhfliy17IcHw$](https://urldefense.com/v3/__https%3A/r20.rs6.net/tn.jsp?f=0010aRHSj9ReFIKfefkO-pdj2aGb8KMbEf5BS4fh7EiqTEvW__dRNtNpU--vPfsFn_-Hh6jcObnqteXpvx6Vp-kzwzCkLpf00DDbItSoEoXYC2CsMwnw3Vb3vMX_WgKjgxmgPdsItwVMaYja4BWR7R5dC3n5ejBY0Qz5OhPEYZI58xo2_wZ7VT7rEGKq1cXzNe4AJzEPcZgfzlQ_4tBK-baVO1ryHs7_ZcESgYcWUdRuMTcYBGynDSvJaEPo_s1TaBmbEy5IGlb4jvqKvJPiMGMiZBsyg8qzBauczka7JEtWT9tpNaYyT3wFNOld0s2UNUiZHHjiQQ5nHQ=&c=vUF_GRJHmONvu5jXhy_OGZzJ_FHVRowK49awbWHqULI1vpK_iBi8pA==&ch=xs2Cy5eCP53j1WvPbDCuCjjYgJIZghYg63Fj3TZF1ClcTna2v9ad7Q==__;!!Db6frn15oIvDD3UI!1kaZaSkRdtNjnvTSxAO6bK2UV6iXRv-Wcs3cU4pCBSxYMehhll0t2nxhfliy17IcHw$)

## Action Items

Task Description Person Responsible Deadline

N/A

Next Meeting: **September 12, 2022** @ 9am CST ZOOM format. Notes: <https://socv.hdiuky.net/>